## Jira Export CSV (all fields) 20
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Attachment | Custom field (Actual end) | Custom field (Actual start) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change type) | Custom field (Development) | Custom field (Epic Color) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Goals) | Custom field (Impact) | Custom field (Issue color) | Custom field (Locked forms) | Custom field (Open forms) | Custom field (Project overview key) | Custom field (Project overview status) | Custom field (Rank) | Custom field (Request Type) | Custom field (Sentiment) | Custom field (Start date) | Custom field (Story Points) | Custom field (Story point estimate) | Custom field (Submitted forms) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Total forms) | Custom field (Vulnerability) | Custom field ([CHART] Date of First Response) | Custom field ([CHART] Time in Status) | Status Category | Status Category Changed
wrong report error in gate pass report | GPS-67 | 10209 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | 2025-01-21 15:40 | 2025-01-21 15:40 | 2025-04-08 23:05 |  |  | 0 |  |  | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | [25 empty] | 0¦i001af: | [13 empty] | To Do | 2025-01-21 15:40
Color Correction in drop down menu in Dark mode | GPS-66 | 10207 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | 2025-01-15 13:33 | 2025-01-15 13:33 |  |  |  | 0 |  |  | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | [25 empty] | 0¦i0019z: | [13 empty] | To Do | 2025-01-15 13:33
Color Correction in drop down menu in Dark mode | GPS-65 | 10206 | Story | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | 2025-01-15 13:32 | 2025-01-15 13:32 |  |  |  | 0 |  |  | Naturub IT Support | 712020:4dd0afc1-0999-4d3a-a95a-578a605460b8 | [25 empty] | 0¦i0019r: | [13 empty] | To Do | 2025-01-15 13:32
auto same int can be inserted into security indexing [ returable] | GPS-64 | 10191 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-16 13:32 | 2024-12-28 12:49 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 28/Dec/24 12:49 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_153.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10170 | [16 empty] | 0¦i0016f: | [13 empty] | To Do | 2024-12-28 12:49
error in decimal value in quantity field | GPS-63 | 10190 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-17 13:32 | 2024-12-28 09:42 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 28/Dec/24 9:42 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_152.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10169 | [16 empty] | 0¦i00167: | [13 empty] | To Do | 2024-12-28 09:42
Error In View Gate Pass Report [ Section ] Individual [ ID] displays all section account | GPS-62 | 10189 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-18 13:32 | 2024-12-28 09:30 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0015z: | [13 empty] | To Do | 2024-12-28 09:30
Vehicle data entry { no data found in security check} | GPS-61 | 10188 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Highest |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-19 13:32 | 2024-12-27 16:51 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0015r: | [13 empty] | To Do | 2024-12-26 19:24
approved gate pass doesn't show in change approval option | GPS-60 | 10187 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | High |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-20 13:32 | 2024-12-27 16:51 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0015j: | [13 empty] | To Do | 2024-12-26 15:52
Error in approval list not showing first approval | GPS-59 | 10186 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-21 13:32 | 2024-12-26 11:56 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 26/Dec/24 11:56 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-26 11-55-08-816.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10168 | [16 empty] | 0¦i0015b: | [13 empty] | To Do | 2024-12-26 11:56
error correction in naming at non -returanable gate pass | GPS-58 | 10185 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-22 13:32 | 2024-12-26 11:46 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 26/Dec/24 11:46 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_151.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10167 | [16 empty] | 0¦i00153: | [13 empty] | To Do | 2024-12-26 11:46
Spare parts data is missing in Returnable gate pass | GPS-57 | 10184 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-23 13:32 | 2024-12-26 11:33 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 26/Dec/24 11:33 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_150.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10166 | [16 empty] | 0¦i0014v: | [13 empty] | To Do | 2024-12-26 11:33
Image and Photo not showing in Vehicle Gate Pass status | GPS-56 | 10183 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-24 13:32 | 2024-12-26 09:51 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 26/Dec/24 9:51 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_149.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10165 | [16 empty] | 0¦i0014n: | [13 empty] | To Do | 2024-12-26 09:50
Gate pass status should be open for all as it's not integrated and user based | GPS-55 | 10182 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-25 13:32 | 2024-12-26 09:35 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0014f: | [13 empty] | To Do | 2024-12-26 09:35
[View gatepass report ] in night mode dropdown menus are not clear visible | GPS-54 | 10181 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | High |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-26 13:32 | 2024-12-25 15:38 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 25/Dec/24 3:38 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_20241225-153803.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10164 | [16 empty] | 0¦i00147: | [13 empty] | To Do | 2024-12-25 15:32
Multiple emp id addition and 1st approval for both id leads to approve both approval for 1st employee | GPS-53 | 10180 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-27 13:32 | 2024-12-25 13:45 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0013z: | [13 empty] | To Do | 2024-12-25 13:45
Sort the gate pass change approver in by date and time wise | GPS-52 | 10179 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-28 13:32 | 2024-12-25 12:07 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0013r: | [13 empty] | To Do | 2024-12-25 12:07
Add a search field in change approver section and fix the pagination button with scroll up button | GPS-51 | 10178 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-29 13:32 | 2024-12-25 12:07 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0013j: | [13 empty] | To Do | 2024-12-25 12:07
Same person can be added multiple times in same gate pass request | GPS-50 | 10177 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-30 13:32 | 2024-12-25 12:35 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 25/Dec/24 12:35 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_147.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10163 | [16 empty] | 0¦i0013b: | [13 empty] | To Do | 2024-12-25 11:48
spelling mistake at medical gate pass | GPS-49 | 10176 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-01-31 13:32 | 2024-12-25 11:44 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 25/Dec/24 11:44 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_146.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10162 | [16 empty] | 0¦i00133: | [13 empty] | To Do | 2024-12-25 11:44
Remove action controller in approve option | GPS-48 | 10175 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-01 13:32 | 2024-12-25 11:22 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0012v: | [13 empty] | To Do | 2024-12-25 11:22
Multiple same employee gate pass request id is accepted in a single request | GPS-47 | 10172 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-02 13:32 | 2024-12-25 12:03 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i00127: | [13 empty] | In Progress | 2024-12-25 09:18
refresh any url link redirect it to profile page | GPS-46 | 10171 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-03 13:32 | 2024-12-25 12:30 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 24/Dec/24 12:52 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-24 12-52-21-952.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10159 | [16 empty] | 0¦i0011z: | [13 empty] | To Do | 2024-12-25 12:30
1st approve twice lead to both approval doesn't redirect it to second approval | GPS-45 | 10170 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-04 13:32 | 2024-12-24 12:48 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 24/Dec/24 12:48 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-24 12-39-48-417.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10158 | [16 empty] | 0¦i0011r: | [13 empty] | To Do | 2024-12-24 12:48
unnecessary pop up message on dummy request save | GPS-44 | 10169 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-05 13:32 | 2024-12-24 12:37 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 24/Dec/24 12:36 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-24 12-35-24-839.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10157 | [16 empty] | 0¦i0011j: | [13 empty] | To Do | 2024-12-24 12:37
Error sorting in date and time wise gate pass show in status and other section | GPS-43 | 10168 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-06 13:32 | 2024-12-24 11:26 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0011b: | [13 empty] | To Do | 2024-12-24 11:26
no request appear in approver gatepass request | GPS-42 | 10167 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-07 13:32 | 2024-12-24 11:16 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 24/Dec/24 11:16 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_145.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10156 | [16 empty] | 0¦i00113: | [13 empty] | To Do | 2024-12-24 11:16
Error In image and name loading in status | GPS-41 | 10166 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-08 13:32 | 2024-12-24 11:13 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 24/Dec/24 11:11 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_144.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10155 | [16 empty] | 0¦i0010v: | [13 empty] | To Do | 2024-12-24 11:13
employee id doesn't clear after addingin new request | GPS-40 | 10165 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-09 13:32 | 2024-12-24 11:00 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 24/Dec/24 11:00 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-24 10-59-47-541.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10154 | [16 empty] | 0¦i0010n: | [13 empty] | To Do | 2024-12-24 11:00
Project title is missing in Gate Pass Home Page | GPS-39 | 10164 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-10 13:32 | 2024-12-24 08:30 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i0010f: | [13 empty] | To Do | 2024-12-24 08:30
Clicking on any option in security link redirect to LOG OUT | GPS-38 | 10163 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-11 13:32 | 2024-12-23 16:45 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i00107: | [13 empty] | To Do | 2024-12-23 16:45
Authentication error As User can access the data with URL link despite of not having the access | GPS-37 | 10162 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-12 13:32 | 2024-12-23 15:32 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000zz: | [13 empty] | To Do | 2024-12-23 15:32
Error Displaying data in security check section | GPS-36 | 10161 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-13 13:32 | 2024-12-23 15:58 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000zr: | [13 empty] | In Progress | 2024-12-23 15:58
Saving the approve request button reject the request from 1st approval's end | GPS-35 | 10160 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Highest |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-14 13:32 | 2024-12-23 16:00 |  |  |  | 0 |  | {noformat}{noformat} {noformat}{noformat} {noformat}{noformat} {noformat}{noformat} | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 23/Dec/24 12:57 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_134.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10153 | [16 empty] | 0¦i000zj: | [13 empty] | In Progress | 2024-12-23 16:00
Multiple person should be visible for multiple gate pass in a single request | GPS-34 | 10159 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | High |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-15 13:32 | 2024-12-25 09:19 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000zb: | [13 empty] | In Progress | 2024-12-25 09:19
Modify the button in approver in correct way | GPS-33 | 10158 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-16 13:32 | 2024-12-23 16:11 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000z3: | [13 empty] | In Progress | 2024-12-23 16:11
Remarks field accept space as character | GPS-32 | 10157 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-17 13:32 | 2024-12-23 12:47 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000yv: | [13 empty] | To Do | 2024-12-23 12:47
Unresponsive in TAB or MOBILE screen size , can't add the new request | GPS-31 | 10156 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-18 13:32 | 2024-12-23 12:06 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 23/Dec/24 12:05 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_20241223-120340.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10152 | [16 empty] | 0¦i000yn: | [13 empty] | To Do | 2024-12-23 12:06
quantity field in returnable gate pass accept 0 and nagtive values | GPS-30 | 10155 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-19 13:32 | 2024-12-23 11:47 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 23/Dec/24 11:47 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_133.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10151 | [16 empty] | 0¦i000yf: | [13 empty] | To Do | 2024-12-23 11:47
Returnable gate pass system - Store > Iteam > items loading is not optimized | GPS-29 | 10154 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-20 13:32 | 2024-12-26 08:40 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 23/Dec/24 11:38 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_132.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10150 | [16 empty] | 0¦i000y7: | [13 empty] | In Progress | 2024-12-26 08:40
Modify the show / hide button , remove the [hide] from the button | GPS-28 | 10153 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-21 13:32 | 2024-12-24 15:32 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 23/Dec/24 11:07 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_131.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10149 | [16 empty] | 0¦i000xz: | [13 empty] | In Progress | 2024-12-24 15:32
Create a new gate pass request doesn't clear the data of existing | GPS-27 | 10152 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-22 13:32 | 2024-12-24 15:19 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 23/Dec/24 8:44 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-23 08-44-08-930.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10148 | [16 empty] | 0¦i000xr: | [13 empty] | In Progress | 2024-12-24 15:19
image loading error in general gate pass | GPS-26 | 10151 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-23 13:32 | 2024-12-24 15:14 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 22/Dec/24 12:34 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_130.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10147 | [16 empty] | 0¦i000xj: | [13 empty] | In Progress | 2024-12-24 15:14
Overlapping of scroll to top and pagination button | GPS-25 | 10149 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-24 13:32 | 2024-12-22 10:55 |  |  |  | 0 |  | {noformat}{noformat} {noformat}{noformat} {noformat}{noformat} {noformat}{noformat} | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 21/Dec/24 3:49 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_129.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10146 | [16 empty] | 0¦i000x3: | [13 empty] | In Progress | 2024-12-22 10:55
Remove the popup in selecting no button and correct the spelling mistake | GPS-24 | 10148 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-25 13:32 | 2024-12-24 15:14 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 21/Dec/24 1:36 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_128.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10145 | [16 empty] | 0¦i000wv: | [13 empty] | In Progress | 2024-12-24 15:14
Error in multiple new gate pass request | GPS-23 | 10145 | Bug | To Do | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-26 13:32 | 2024-12-24 15:46 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000w7: | [13 empty] | To Do | 2024-12-24 15:46
infinite popup error message displaying in entry report | GPS-22 | 10144 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-27 13:32 | 2024-12-19 16:52 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 18/Dec/24 4:31 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-18 16-30-39-304.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10142 | [16 empty] | 0¦i000vz: | [13 empty] | In Progress | 2024-12-19 16:52
increment button functionality without content | GPS-21 | 10143 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-02-28 13:32 | 2024-12-19 16:52 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 18/Dec/24 4:04 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-18 15-56-13-183.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10141 | [16 empty] | 0¦i000vr: | [13 empty] | In Progress | 2024-12-19 16:52
same person for the 1st and 2nd approval doesn't appeare after 1st approval | GPS-20 | 10142 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-01 13:32 | 2024-12-24 13:42 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000vj: | [13 empty] | In Progress | 2024-12-24 13:42
1st approval remarks and 2nd approval remarks are entitling same message | GPS-19 | 10141 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-02 13:32 | 2024-12-24 13:20 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 18/Dec/24 1:43 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_126.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10140 | [16 empty] | 0¦i000vb: | [13 empty] | In Progress | 2024-12-24 13:20
Remarks field takes blank space data , should be corrected | GPS-18 | 10140 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-03 13:32 | 2024-12-24 13:04 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 18/Dec/24 12:00 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-18 11-58-56-994.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10139 | [16 empty] | 0¦i000v3: | [13 empty] | In Progress | 2024-12-24 13:04
cancelation of create new user remove may save successfully popup display | GPS-17 | 10139 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-04 13:32 | 2024-12-24 12:48 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 18/Dec/24 11:55 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-18 11-54-52-560.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10138 | [16 empty] | 0¦i000uv: | [13 empty] | In Progress | 2024-12-24 12:48
Add search bar in audit approval | GPS-16 | 10138 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-05 13:32 | 2024-12-24 12:37 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 18/Dec/24 11:09 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_125.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10137 | [16 empty] | 0¦i000un: | [13 empty] | In Progress | 2024-12-24 12:37
No data is displayed on status tab after create a new request | GPS-15 | 10137 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-06 13:32 | 2024-12-24 12:31 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000uf: | [13 empty] | In Progress | 2024-12-24 12:31
misplaced of page in status section | GPS-14 | 10136 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-07 13:32 | 2024-12-19 08:28 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 4:52 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_124.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10136 | [16 empty] | 0¦i000u7: | [13 empty] | In Progress | 2024-12-19 08:28
missing Display in and out time in audit approval | GPS-13 | 10135 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-08 13:32 | 2024-12-24 12:30 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [25 empty] | 0¦i000tz: | [13 empty] | In Progress | 2024-12-24 12:30
side bar dynamic menu icon modification | GPS-12 | 10134 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-09 13:32 | 2024-12-24 09:54 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 3:52 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_123.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10135 | [16 empty] | 0¦i000tr: | [13 empty] | In Progress | 2024-12-24 09:54
Minimum character should be implemented in remarks field | GPS-11 | 10132 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-10 13:32 | 2024-12-24 09:55 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 1:19 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_120.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10132 | [16 empty] | 0¦i000tb: | [13 empty] | In Progress | 2024-12-24 09:55
request can be done without prior permission or access from KPI | GPS-10 | 10131 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-11 13:32 | 2024-12-24 12:24 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 1:12 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_119.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10131 | [16 empty] | 0¦i000t3: | [13 empty] | In Progress | 2024-12-24 12:24
Cancelletion of create new user arise the category section | GPS-9 | 10130 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-12 13:32 | 2024-12-18 15:49 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 12:55 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-15 12-53-15-208.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10130 | [16 empty] | 0¦i000sv: | [13 empty] | In Progress | 2024-12-18 15:49
Unnecessary footer items remove in gate pass system | GPS-8 | 10129 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-13 13:32 | 2024-12-18 12:24 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 12:48 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_118.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10129 | [16 empty] | 0¦i000sn: | [13 empty] | In Progress | 2024-12-18 12:24
misplacement of id in create new user | GPS-7 | 10128 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-14 13:32 | 2024-12-18 12:09 |  |  |  | 0 |  | {noformat}{noformat} | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 12:43 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_117.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10128 | [16 empty] | 0¦i000sf: | [13 empty] | In Progress | 2024-12-18 12:09
select a new gate pass type have UI and alignment issue | GPS-6 | 10127 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-15 13:32 | 2024-12-18 12:03 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 12:24 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_116.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10127 | [16 empty] | 0¦i000s7: | [13 empty] | In Progress | 2024-12-18 12:03
Expandable menu open multiple at one time | GPS-5 | 10126 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-16 13:32 | 2024-12-18 11:32 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 12:18 PM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;bandicam 2024-12-15 12-10-53-476.mp4;https://naturub.atlassian.net/rest/api/3/attachment/content/10126 | [16 empty] | 0¦i000rz: | [13 empty] | In Progress | 2024-12-18 11:32
Re-directing to home page is missing correct it | GPS-4 | 10125 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-17 13:32 | 2024-12-18 11:26 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 11:48 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_115.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10125 | [16 empty] | 0¦i000rr: | [13 empty] | In Progress | 2024-12-18 11:26
Correction of expandble button and dark mode button | GPS-3 | 10124 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-18 13:32 | 2024-12-18 11:23 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 11:42 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_114.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10124 | [16 empty] | 0¦i000rj: | [13 empty] | In Progress | 2024-12-18 11:23
Header error on gate pass system | GPS-2 | 10123 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-19 13:32 | 2024-12-18 10:07 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 11:31 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_113.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10123 | [16 empty] | 0¦i000rb: | [13 empty] | In Progress | 2024-12-18 10:07
Wrong popup message display inputting wrong password | GPS-1 | 10122 | Bug | In Progress | GPS | Gate Pass System | software | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c |  | Medium |  |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | 2025-03-20 13:32 | 2024-12-18 09:04 |  |  |  | 0 |  |  | NATURUB | 712020:8f6a40b7-7b4e-4802-b896-7433d26f561c | [8 empty] | 15/Dec/24 11:09 AM;712020:8f6a40b7-7b4e-4802-b896-7433d26f561c;Screenshot_111.png;https://naturub.atlassian.net/rest/api/3/attachment/content/10122 | [16 empty] | 0¦i000r3: | [13 empty] | In Progress | 2024-12-18 09:04